## Sprint 1
tag | blocks / prerequistes | As a.. | I want.. | So that... | Effort | Mockup | Owner | Notes
frontend-admin |  | unit_coordinator | to have an admin page on frontend(only for unit_coordinator) | i can have access to the 'upload excel file' button on my frontend page | 1 | Done | Ollie
frontend-upload-1 |  | unit_coordinator | to upload an excel file (to the front end) | I can see all the course information | 3 | Working on | Ollie | this is cleaning / parsing the data
frontend-upload-2 |  | unit_coordinator | to see a confirmation that the excel uploaded | i know the data was sent to the backend
backend-api-1 |  | developer | to make available the course title via POST api (MiT) | the front end can access it | 1 | Done | Ollie | /api/v1/courses - we believe POST request would be more secure to return data, so crawlers cannot find GET requests
backend-api-2 |  | developer | to make available the unit titles via POST api | the front end can access it | 1 |  |  | POST request
backend-api-3 |  | developer | to delete a course via DELETE api | the front end can access it | 1
frontend-1 | backend-api-1 | unit_coordinator | to see the available courses (from the POST request) |  | 2

## Sprint 2
tag | blocks | As a.. | I want.. | So that... | Mockup | Owner | Notes
plan-1 |  | user | to see all units in 1 view | I can verify all units have been imported
plan-2 | plan-1 | user | drag and drop my units into semesters | I can start to plan out my semester
plan-3 | plan-1 | user | to disallow dropping a s2 unit into a s1 slot (visa-versa) | I cannot create an invalid unit plan
plan-4 | plan-1 | user | to disallow dropping too many units into a semester | I cannot create an invalid unit plan
api-1 |  | dev | to access the data via the api | i can present it onto the screen
frontend-admin2 |  | unit_coordinator | to create / delete logins for more staff members | they can have access to the unit details on the backend | 1 |  |  | This functionality has been implemented
frontend-delete-1 |  | unit_coordinator | to delete a course that has been uploaded via a "delete form" | i no longer see it | 2

## Sprint 3
tag | blocks | As a.. | I want.. | So that... | Mockup | Owner | Notes
export-1 |  | User | To save (export) my unit plan | I can continue working on my plan later |  |  | csv? json? xls?
import-1 |  | user | To import my saved unit plan | I can continue working on my unit plan

## Low-urgency
tag | blocks | As a.. | I want.. | So that... | Mockup | Owner | Notes
|  | User | to auto-generate my unit plan
|  | User | I can randomize my current unit plan
|  | User | I can undo my last move(s) | I am not stressed about making mistakes
|  | User | I can save my plan online (publicly) | Others can see my plan, and i can resume it later |  |  | Name (not unique), created date, created by?